MarketMind

4-Week Team Execution Plan

4-Person Team — Independent Module Ownership, Day-0 Parallel Start

Walchand College of Engineering, Sangli

# 1. Team and Skill Mapping

| Member | Strengths (as stated) | Primary module |
| --- | --- | --- |
| Alok Kulkarni | Frontend, backend, DB, implementing AI through APIs | Backend Analytics/API layer + DB schema ownership |
| Niharika | Frontend | Frontend |
| Piyush Dawkhare | Cloud, backend, a little ML | Cloud & Data Ingestion (+ ML assist to Rajurkar from Day 0) |
| Piyush Rajurkar | ML (strongest on the team) | Price ML + BERT Sentiment + RAG Causal Engine (sequential, all three stages) |

No fixed team lead — coordination rotates. The Day 0 contract (Section 3) and this plan are what keep everyone unblocked, not a designated leader.

# 2. Timeline and Scope Constraints

Deadline: 4 weeks for the complete deliverable — working MVP, evaluation, and final report. One agreed flex: BERT fine-tuning may spill a few extra days into Week 2–3 if genuinely needed; every other module holds the 4-week line.

Stock universe: kept at the original 20–25 NSE-listed stocks across 4–5 sectors, 2–5 years of historical depth.

Everyone starts Day 0: no dedicated setup-only week. A single kickoff session on Day 0 gives every person what they need to start building independently the same day.

Honest scope note: 20–25 stocks, real fine-tuning, full evaluation, and a full report inside 4 weeks is genuinely tight. Section 4 splits features into Core (committed) and Stretch (only if time remains) so the team commits honestly rather than overcommitting silently.

# 3. Day 0: The Shared Contract

Owner: Alok Kulkarni pre-drafts the DB schema and core API contract before Day 0 (not during it), so the whole team can start the same morning.

Day 0 kickoff (2–3 hours) delivers:

- Finalized PostgreSQL schema (instruments, price_history, news_articles, anomaly_events, explanations, etc.) — presented and locked, changes after this point go through a quick team check rather than one person deciding alone.

- API endpoint contracts (request/response JSON shapes) for: stock data, anomaly/regime, sentiment, causal explanation, comparison.

- A small hand-prepared sample dataset (a few rows per table) so Alok, Niharika, and Rajurkar can build against real-shaped data immediately, without waiting on Dawkhare's full ingestion pipeline.

- Team agreement on the Core vs Stretch split (Section 4).

- Niharika starts from the existing MarketMind frontend prototype (the ledger-dossier HTML mockup already built) rather than a blank project — converting a working design into components is faster than designing from scratch.

This replaces a dedicated setup week: the contract exists before the clock starts, so nobody spends Week 1 waiting.

# 4. Core vs Stretch Scope

| Core (committed, must ship in 4 weeks) | Stretch (only if Week 4 has slack, else future work in report) |
| --- | --- |
| Data ingestion: 20–25 stocks, price + news, 2–5 yr history | Portfolio-linked alerts (standalone watchlist) |
| Statistical anomaly/regime detection (z-score, excess return) | Event calendar / watch-factor markers |
| Price-pattern classifier (XGBoost/LightGBM) | Sector heatmap view |
| Fine-tuned BERT sentiment + causal-category model | PDF report export |
| Signal-agreement layer (price vs sentiment) | Volatility/risk snapshot (beta, vol percentile) |
| Time-aligned RAG retrieval + causal synthesis with citations/abstention | Contrarian check (2 competing explanations) |
| Single-stock query flow, end-to-end, in the frontend | Confidence-over-time trend |
| Basic peer/sector comparison (2–4 stocks) | Query history / saved searches |
| Explainability trail (retrieved sources shown — cheap, since RAG already returns them) |  |
| Historical accuracy scoreboard (single stat from backtest — cheap to expose) |  |
| Backtest evaluation (≈15 historical events) + human rubric |  |
| Final report |  |

# 5. Technical Architecture

Backend in Spring Boot (Java). Since Rajurkar's ML and RAG work is realistically Python (XGBoost, BERT fine-tuning, LLM API calls), the architecture separates concerns cleanly:

| Layer | Technology | Owner |
| --- | --- | --- |
| Frontend | React + Vite + TypeScript + Tailwind, built from the existing prototype | Niharika |
| Backend/API orchestration | Spring Boot (Java) | Alok Kulkarni |
| Database | PostgreSQL + pgvector (schema fixed Day 0) | Alok Kulkarni (design), all (usage) |
| ML/RAG microservice | Python + FastAPI (internal service, called by Spring Boot) | Piyush Rajurkar |
| Ingestion scripts | Python (scheduled/batch jobs) | Piyush Dawkhare |
| Cloud/deployment | Cloud hosting for all services + CI/CD | Piyush Dawkhare |

The Spring Boot backend calls the Python ML/RAG microservice over an internal REST API defined in the Day 0 contract — Alok's module only needs to know that contract, not Rajurkar's internal implementation, which is what keeps the two modules independent.

# 6. Why Everyone Can Work Independently

The goal is that all four people work in parallel for the full 4 weeks without waiting on each other. This holds because of one rule: everyone builds against the Day 0 contract and sample data, swapping mocks for real integrations incrementally as each module lands — never blocking on another module being finished.

- Niharika builds the frontend against mock JSON matching the agreed API shapes — she never needs the backend running to make progress.

- Alok builds backend analytics against the schema he defined, using the sample dataset and stubbed ML outputs — he doesn't wait for full ingestion or trained models.

- Dawkhare builds ingestion against the same fixed schema independently.

- Rajurkar builds and trains models starting from a small hand-prepared sample on Day 0, then swaps to Dawkhare's real ingested data once available.

The one genuine sequential dependency in this plan is inside Rajurkar's own module (price classifier → BERT → RAG) — a deliberate, accepted trade-off given he owns all three ML stages. It is mitigated by starting Stage 1 immediately on Day 0 and by Dawkhare's ML-assist role beginning the same day rather than later.

# 7. Module Responsibilities

## Alok Kulkarni — Backend Analytics/API + DB Schema

- Day 0: present pre-drafted DB schema + API contracts to the team.

- Spring Boot service setup: auth, Caffeine caching, rate limiting.

- Statistical anomaly/trend detection logic (rolling z-score on returns/volume, excess return vs benchmark index), built against sample data from Day 0.

- Peer/sector comparison endpoint.

- Integration layer: connects to Dawkhare's ingested data (via DB) and Rajurkar's ML/RAG microservice (via internal API) as each becomes ready — works against stubbed responses matching the contract until then.

- Watchlist table and alert logic if Core work finishes with time to spare.

## Niharika — Frontend

- Day 0: convert the existing ledger-dossier prototype into React components; set up project against mock JSON matching the API contract.

- Query bar, price chart, result dossier layout, signal-agreement badge, sentiment trend line.

- Explanation panel with cited sources (explainability trail) and confidence indicator.

- Peer/sector comparison view.

- Swap mock data for live API calls incrementally as Alok's endpoints go live — no rework needed since the contract was fixed Day 0.

- Historical accuracy scoreboard display (Core-lite) once Rajurkar's backtest numbers exist.

## Piyush Dawkhare — Cloud & Data Ingestion (+ ML assist from Day 0)

- Day 0 onward: build price/NAV fetchers (NSE Security-wise Archives or yfinance) and news/RSS scrapers, writing into the Day-0 schema — target full 20–25 stock price coverage by end of Week 1, since everyone else depends on this data.

- Entity/sector mapping table.

- Data cleaning, deduplication, timestamp normalization; validate a sample against official NSE data.

- Cloud setup and CI/CD for all services (backend, ML microservice, frontend) so the team can deploy independently.

- ML-assist role starts Day 0, not after ingestion stabilizes: split time between ingestion and supporting Rajurkar on feature engineering (moving averages, RSI, volatility) for the price-pattern classifier, since Dawkhare owns the underlying data.

- In Week 2–3, help identify the ~15 historical events needed for backtest evaluation, so Week 4 only has to run the rubric, not also research events.

## Piyush Rajurkar — Price ML + BERT Sentiment + RAG Causal Engine

- Day 0–3: price-pattern classifier (XGBoost/LightGBM) on a small hand-pulled sample while full ingestion completes, regime classification (bullish/bearish/consolidating); switch to full data once Dawkhare's pipeline lands.

- In parallel from Day 0: start LLM-bootstrapped labeling for the BERT sentiment/causal-category dataset (doesn't require price data, can run concurrently).

- Week 2: fine-tune BERT (sentiment + causal category heads) — the one piece allowed to spill a few extra days if needed; begin RAG retrieval plumbing (pgvector, time-filtering) in parallel where it doesn't depend on BERT being fully done.

- Week 3: complete signal-agreement layer (price regime vs BERT sentiment) and RAG causal synthesis prompt (citations, abstention behavior); expose all three stages via the FastAPI microservice per the Day 0 contract.

- Week 4: run backtest evaluation (~15 historical events), report accuracy/F1 for both ML models and rubric scores for RAG explanations.

# 8. Week-by-Week Plan

| Days | Alok | Niharika | Dawkhare | Rajurkar |
| --- | --- | --- | --- | --- |
| Day 0 | Present pre-drafted schema/contract + sample data | Attend kickoff; set up repo from existing prototype | Attend kickoff; cloud env setup begins same day | Attend kickoff; pull first sample stock data manually to start immediately |
| Days 1–7 (Wk1) | Spring Boot skeleton, auth, caching, anomaly detection logic on sample data | Convert prototype into React components; wire to mock JSON | Price/news fetchers live for full 20–25 stock list by end of week; afternoons: feature engineering support for Rajurkar | Train price-pattern classifier on manual sample → real data as it lands; start LLM-bootstrapped sentiment labeling in parallel |
| Days 8–14 (Wk2) | Comparison + integrate real ingestion data; stub ML endpoints per contract | Explanation panel, agreement badge, sentiment trend UI against stubs | Finish full ingestion + entity/sector mapping; CI/CD; continue ML assist | BERT fine-tuning (flex days allowed here if needed); start RAG retrieval plumbing in parallel |
| Days 15–21 (Wk3) | Integrate ML/RAG microservice endpoints as they land; watchlist stub if time | Replace all mocks with live API calls; polish core screens | Backtest event research support; deployment stability | Finish BERT if spilled; complete signal-agreement + RAG causal synthesis; expose via API |
| Days 22–28 (Wk4) | Integration testing, bug fixes, report section | Integration testing, explainability trail + scoreboard UI, report section | Integration testing, final deployment, report section | Run backtest evaluation, report metrics, report section |

# 9. Dependency Map

| Dependency | Type | Mitigation |
| --- | --- | --- |
| Everyone → Alok's Day 0 schema/contract | One-time, upfront | Pre-drafted before Day 0 so it's ready the same morning; treated as fixed after that |
| Alok's real data → Dawkhare's ingestion | Ongoing, soft | Alok develops against sample data first; swaps to live data incrementally, no interface change |
| Niharika's live API → Alok's endpoints | Ongoing, soft | Niharika develops against mock JSON matching the contract; swaps to live calls incrementally |
| Rajurkar's BERT/RAG → his own price classifier | Sequential, hard (accepted) | Stage 1 starts Day 0 on sample data; Dawkhare's assist starts Day 0 too, reducing load; fine-tuning has explicit flex days |
| Alok's ML integration → Rajurkar's microservice | Ongoing, soft | Alok stubs ML responses matching the Day 0 contract until real endpoints land |

# 10. Risk Flags Specific to This Compressed Plan

- Rajurkar's three-stage ML chain (price → BERT → RAG) is the tightest path in the whole plan — if BERT fine-tuning spills past its flex allowance, RAG synthesis in Week 3 is directly at risk. Check in specifically at the end of Week 2.

- Full 20–25 stock ingestion in Week 1 alone is ambitious — if NSE/news sources are slow or rate-limited, prioritize full price coverage first (everyone depends on it) and treat full news-corpus depth as extensible into Week 2.

- Evaluation (backtest + rubric) is scheduled in Week 4 — if integration testing runs long, evaluation is most at risk of compression. Identifying the ~15 backtest historical events during Week 2–3 (Dawkhare's task) means Week 4 only has to run the rubric, not also research events.

- There is no dedicated buffer week — Week 4 carries both integration and report-writing. If anything slips, the Stretch list (Section 4) is what gets cut first, not Core features or evaluation.

# 11. Individual Contribution Clarity (for Evaluation)

- Alok: working Spring Boot backend with defined schema, anomaly detection logic, and integration layer — demonstrable independently via API calls and DB inspection.

- Niharika: working frontend that functions end-to-end against mock data even if backend/ML pieces are incomplete — demonstrable as a standalone UI walkthrough.

- Dawkhare: working ingestion pipeline with validated data quality, plus cloud deployment setup — demonstrable via live data pulls and deployment dashboard.

- Rajurkar: three trained/evaluated ML components (price classifier, BERT sentiment model, RAG synthesis) with reported metrics — demonstrable via evaluation reports and example query outputs.

Git commit history naturally segments by module/folder ownership — worth citing to your guide as evidence of individual contribution alongside this document.

# 12. Final Notes

- No fixed team lead by team choice — the Day 0 contract replaces the need for a single coordinating authority; scope disagreements get resolved via a short team sync, not unilateral decisions.

- Rajurkar owning all three ML/RAG stages sequentially is a deliberate, informed trade-off — revisit at the Week 2 checkpoint if the price classifier and BERT stages are behind, since Dawkhare's assist role could expand further if needed.

- This plan assumes the standalone-watchlist design (no external Asset Hub integration) discussed earlier, and the 20–25 stock curated universe from the main project scope document.