MarketMind

Team Workload Distribution Plan

4-Person Team — Independent Module Ownership Design

Walchand College of Engineering, Sangli

# 1. Team and Skill Mapping

| Member | Strengths (as stated) | Primary module |
| --- | --- | --- |
| Alok Kulkarni | Frontend, backend, DB, implementing AI through APIs | Module C — Backend Analytics/API layer + DB schema ownership |
| Niharika | Frontend | Module D — Frontend |
| Piyush Dawkhare | Cloud, backend, a little ML | Module A — Cloud & Data Ingestion (+ assists Module B) |
| Piyush Rajurkar | ML (strongest on the team) | Module B — Price ML + BERT Sentiment + RAG Causal Engine |

No fixed team lead — coordination rotates. This document exists precisely so that no single person needs to be a bottleneck for direction: the module boundaries and the Week 1 contract (Section 3) are what keep everyone unblocked, not a designated leader.

# 2. Design Philosophy: Independent, Contract-First Modules

The explicit goal is that all four people can work in parallel for most of the semester without waiting on each other. This is achieved with one rule: in Week 1, the team agrees on a fixed data contract (DB schema + API request/response shapes) and everyone builds against that contract using mock/sample data until the real upstream module is ready — then swaps mock for real with no interface change.

- Niharika builds the frontend against hand-written mock JSON matching the agreed API shapes — she never needs the backend running to make progress.

- Alok builds backend analytics against the DB schema he defines, using a small sample dataset and stubbed ML outputs — he doesn't wait for Piyush Dawkhare's full ingestion pipeline or Piyush Rajurkar's trained models.

- Piyush Dawkhare builds ingestion against the same schema independently — his output format is fixed by the Week 1 contract, so he doesn't need to coordinate with Alok beyond that.

- Piyush Rajurkar builds and trains models against a small hand-prepared sample dataset early, then swaps to Piyush Dawkhare's real ingested data once available — he is not blocked waiting for ingestion to be perfect.

The one genuine sequential dependency in this design is inside Module B itself (price model → BERT → RAG, all owned by Piyush Rajurkar, as agreed) — this is a real, accepted trade-off, addressed directly in Section 5.

# 3. Week 1: The Shared Contract

Owner: Alok Kulkarni defines the DB schema and core API contract upfront, in the first week, before other modules begin substantial work.

Deliverables from this week, shared with the whole team:

- Finalized PostgreSQL schema (instruments, price_history, news_articles, anomaly_events, explanations, etc.)

- API endpoint contracts (request/response JSON shapes) for: get stock data, get anomaly/regime, get sentiment, get causal explanation, comparison endpoint

- A small shared sample dataset (a handful of rows per table) that every module can develop against immediately

This is a working document, not fixed in stone — but changes after Week 1 should be proposed and agreed by the team briefly, since three other people's modules depend on it.

# 4. Recommended Technical Architecture

Backend confirmed as Spring Boot (Java). Since Piyush Rajurkar's ML and RAG work is realistically Python (XGBoost, HuggingFace/BERT fine-tuning, LLM API calls), the recommended architecture separates concerns cleanly:

| Layer | Technology | Owner |
| --- | --- | --- |
| Frontend | React + Vite + TypeScript + Tailwind | Niharika |
| Backend/API orchestration | Spring Boot (Java) | Alok Kulkarni |
| Database | PostgreSQL + pgvector (schema defined Week 1) | Alok Kulkarni (design), all (usage) |
| ML/RAG microservice | Python + FastAPI (internal service, called by Spring Boot) | Piyush Rajurkar |
| Ingestion scripts | Python (scheduled jobs) | Piyush Dawkhare |
| Cloud/deployment | Cloud hosting for all services + CI/CD | Piyush Dawkhare |

The Spring Boot backend calls the Python ML/RAG microservice over an internal REST API, the same way it would call any other internal service — this means Alok's Module C work only needs to know the ML service's request/response contract (defined Week 1), not its internal implementation, which is exactly the independence the team asked for.

# 5. Module Breakdown and Responsibilities

## Alok Kulkarni — Module C: Backend Analytics/API Layer + DB Schema

- Week 1: define and circulate DB schema + API contracts for the whole team.

- Spring Boot service setup: auth, Caffeine caching, rate limiting.

- Statistical anomaly/trend detection logic (rolling z-score on returns/volume, excess return vs benchmark index) — develop against the Week 1 sample dataset.

- Peer/sector comparison endpoint and volatility/risk snapshot endpoint.

- Integration layer: calls Piyush Dawkhare's ingested data (via DB) and Piyush Rajurkar's ML/RAG microservice (via internal API) once each is ready — until then, works against stubbed responses matching the agreed contract.

- Watchlist table and alert-triggering logic (standalone, no external portfolio-app dependency).

## Niharika — Module D: Frontend

- React + Vite + TypeScript dashboard: query bar, price chart, explanation panel — built against mock JSON matching the Week 1 API contract from day one, so no dependency on backend progress.

- Signal-agreement badge UI, sentiment trend visualization, explainability trail (collapsible source list).

- Peer/sector comparison view and historical pattern-match display.

- Side features owned here: historical accuracy scoreboard display, event calendar markers, PDF report export.

- Swap mock data for live API calls incrementally as Alok's endpoints go live — no rework needed since the contract was fixed in Week 1.

## Piyush Dawkhare — Module A: Cloud & Data Ingestion (+ ML assist)

- Week 1 onward: build price/NAV fetchers (NSE Security-wise Archives or yfinance) and news/RSS scrapers, writing into the schema Alok defined — independent of anyone else's progress once the schema is fixed.

- Entity/sector mapping table and event calendar data (earnings dates, RBI policy, Union Budget).

- Data cleaning, deduplication, timestamp normalization; validate a sample against official NSE data.

- Cloud setup: hosting/deployment pipeline for all services (Spring Boot backend, Python ML microservice, frontend), plus CI/CD so the team can deploy independently without manual coordination.

- ML assist role (secondary, after ingestion is stable): support Piyush Rajurkar on the price-pattern classifier specifically — feature engineering from OHLCV data (moving averages, RSI, volatility) is the natural handoff point, since Dawkhare owns the data those features come from.

## Piyush Rajurkar — Module B: Price ML + BERT Sentiment + RAG Causal Engine

- Stage 1 — Price-pattern classifier: feature engineering (with Dawkhare's assist) and XGBoost/LightGBM regime classification (bullish/bearish/consolidating), trained initially on a small sample dataset, later on Dawkhare's full ingested history.

- Stage 2 — Fine-tuned BERT sentiment/category model: label a news/social dataset (LLM-assisted bootstrap + manual review), fine-tune for sentiment + causal category, evaluate with accuracy/F1/confusion matrix.

- Stage 3 — Signal fusion + RAG synthesis: combine price regime and BERT sentiment into the agreement layer; build time-aligned retrieval (pgvector) with hard timestamp filtering; write the causal synthesis LLM prompt with citation and abstention behavior.

- Expose all three stages via the Python FastAPI microservice, against the Week 1 contract, so Alok's backend can integrate incrementally as each stage completes.

This is explicitly a sequential, single-owner chain by team agreement. It is the one place in the plan where later work depends on earlier work by the same person — mitigated by starting Stage 1 immediately in Week 1–2 against sample data, and by Piyush Dawkhare's assist role reducing Stage 1's workload.

# 6. Timeline (15 Weeks, Parallel Tracks)

| Week | Alok (Backend/DB) | Niharika (Frontend) | Dawkhare (Cloud/Ingestion) | Rajurkar (ML/RAG) |
| --- | --- | --- | --- | --- |
| 1 | Define DB schema + API contracts | Set up project, mock data scaffolding | Cloud environment setup | Review contract, plan feature set |
| 2–3 | Spring Boot skeleton, auth, caching | Query bar + chart UI against mocks | Price/news fetchers built and running | Feature engineering (with Dawkhare), sample-data prototyping |
| 4–6 | Anomaly detection logic (z-score, excess return) | Explanation panel + agreement badge UI | Data cleaning, validation, entity/sector mapping | Train price-pattern classifier; begin sentiment dataset labeling |
| 7–9 | Comparison + risk snapshot endpoints; integrate real ingestion data | Comparison view, sentiment trend line, pattern-match display | Event calendar data; CI/CD setup; support Rajurkar on features | Fine-tune BERT model; evaluate metrics |
| 10–11 | Integrate ML/RAG microservice endpoints as they land | Wire live API calls in place of mocks | Deploy all services to cloud; monitor pipeline | Build signal-agreement layer + RAG retrieval/synthesis |
| 12–13 | Watchlist/alerts; bug fixes | Side features: PDF export, explainability trail polish | Backtest data support; deployment stability | Backtest evaluation of RAG explanations |
| 14–15 | Integration testing, report section | Integration testing, report section | Integration testing, report section | Integration testing, report section |

# 7. Dependency Map

| Dependency | Type | Mitigation |
| --- | --- | --- |
| Everyone → Alok's Week 1 schema/contract | One-time, upfront | Delivered in Week 1 before other modules need it; treated as fixed after that |
| Alok's real data → Dawkhare's ingestion | Ongoing, soft | Alok develops against sample data first; swaps to live data incrementally, no interface change |
| Niharika's live API → Alok's endpoints | Ongoing, soft | Niharika develops against mock JSON matching the contract; swaps to live calls incrementally |
| Rajurkar's BERT/RAG → his own price classifier | Sequential, hard (accepted) | Start Stage 1 immediately in Week 1–2 on sample data; Dawkhare's assist reduces Stage 1 load; buffer weeks 14–15 absorb slippage |
| Alok's ML integration → Rajurkar's microservice | Ongoing, soft | Alok stubs ML responses matching the Week 1 contract until real endpoints land |

# 8. Individual Contribution Clarity (for Evaluation)

Each person's module produces an independently demonstrable artifact, useful for viva and individual assessment:

- Alok: working Spring Boot backend with defined schema, anomaly detection logic, and integration layer — demonstrable via API calls and DB inspection independent of the other three modules being complete.

- Niharika: working frontend that functions end-to-end against mock data even if backend/ML pieces are incomplete — demonstrable as a standalone UI walkthrough.

- Piyush Dawkhare: working ingestion pipeline with validated data quality, plus cloud deployment setup — demonstrable via live data pulls and deployment dashboard.

- Piyush Rajurkar: three trained/evaluated ML components (price classifier, BERT sentiment model, RAG synthesis) with reported metrics — demonstrable via model evaluation reports and example query outputs.

Git commit history naturally segments by module/folder ownership, which is worth mentioning to your guide as evidence of individual contribution alongside this document.

# 9. Notes

- No fixed team lead by team choice — the Week 1 contract is what replaces the need for a single coordinating authority; if scope disagreements arise later, a short team sync resolves them rather than one person deciding unilaterally.

- Piyush Rajurkar owning all three ML/RAG stages sequentially was a deliberate, informed trade-off — revisit at the Week 6–7 checkpoint if the price classifier and BERT stages are running behind, since Dawkhare's assist role could expand if needed.

- This plan assumes the previously discussed standalone-watchlist design (no external Asset Hub integration) and the 20–25 stock curated universe from the main project document.